## Goods
Country: NIGERIA
Program: ACE IMPACT
Date: DECEMBER, 2024
Applicable Period: JANUARY, 2025 - JUNE, 2025
Project ID: ACEMFS FUT, Minna
| Implementing Agency: NUC, NIGERIA | [7 empty] | Draft Bid Documents, including specs and quantities, draft SPN
|  |  | BASIC DATA | [7 empty] | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation |  |  | Contract Finalization |  |  |  |  | Contract Implementation
| Description* | Package Number | Number of Lots | Estimated Amount in US $ | Procurement Method | Pre-or Post Qualification | Prior or Post Review | Plan vs. Actual | Prep & Submission by Ex Agency | No-objection Date | On-line UNDB Gateway Nat Press | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | No-objection Date | Plan vs. Actual | Contract Amount in US$ | Date Contract Award | Date Contract Advert | Date Contract Signature | Opening of Let of Credit | Arrival of Goods | Inspection Final Acceptance | Remarks
| Norm Duration of Proc Steps |  |  |  |  | If Prequalification |  | Plan | 4 - 7 wks | 1 - 1.5 wks | 1.5 - 2 wks | 4 to | 6 wks | 1.5 - 3 wks | 1 - 1.5 wks | Plan |  | 1 wk |  | 1.5-3 wks
[6 empty] | add 7-13 wks |  | Actual | [7 empty] | Actual
List of Contracts
1 | Procurement of a digital camera to cover all Centre events | FUTM/ACEMFS/GDS/NS/2025/1 | 1 | 3000 | NS | Post Qualification | Post Review |  | 24-Jan-25 | 27-Jan-25 | NA | 27-Jan-25 | 10-Feb-25 | 14-Feb-25 | 17-Feb-25 | Plan | 3000 | 17-Feb-25 | 17-Feb-25 | 07-Mar-25 | N/A | 11-Mar-25 | 11-Mar-25
[16 empty] | Actual |  |  |  |  | NA
2 | Production of Manuals and Students Handbook | FUTM/ACEMFS/GDS/NS/2025/02 | 1 | 5000 | NS | Post Qualification | Post Review | Plan | 24-Jan-25 | 27-Jan-25 | NA | 27-Jan-25 | 10-Feb-25 | 14-Feb-25 | 17-Feb-25 | Plan | 5000 | 17-Feb-25 | 17-Feb-25 | 07-Mar-25 | N/A | 11-Mar-25 | 11-Mar-25
[8 empty] | Actual | [7 empty] | Actual
3 | Provide adequate teaching materials and facilities for Food Safety, Molecular Biology and Bioinformatics,and Toxicology | FUTM/ACEMFS/GDS/NS/2025/03 | 3 | 5000 | NS | Post Qualification | Post Review | Plan | 24-Jan-25 | 27-Jan-25 | NA | 27-Jan-25 | 10-Feb-25 | 14-Feb-25 | 17-Feb-25 |  | 5000 | 17-Feb-25 | 17-Feb-25 | 07-Mar-25 | N/A | 11-Mar-25 | 11-Mar-25
Actual
4 | Procurement of Inverter battery cells/Accessoriesfor electricity generation | FUTM/ACEMFS/GDS/NS/2025/04 | 1 | 10000 | NS | Post Qualification | Post Review | Plan | 24-Jan-25 | 27-Jan-25 | NA | 27-Jan-25 | 10-Feb-25 | 14-Feb-25 | 17-Feb-25 | Plan | 10000 | 17-Feb-25 | 17-Feb-25 | 07-Mar-25 | N/A | 11-Mar-25 | 11-Mar-25
Actual
5 | Office supplies and equipment maintenace | FUTM/ACEMFS/GDS/NS/2025/05 | 1 | 10000 | NS | Post Qualification | Post Review | Plan | 24-Jan-25 | 27-Jan-25 | NA | 27-Jan-25 | 10-Feb-25 | 14-Feb-25 | 17-Feb-25 | Plan | 10000 | 17-Feb-25 | 17-Feb-25 | 07-Mar-25 | N/A | 11-Mar-25 | 11-Mar-25
[8 empty] | Actual | [7 empty] | Actual
6 | Procurement of Office equipment and consumables | FUTM/ACEMFS/GDS/NS/2025/06 | 3 | 10000 | NS | Post Qualification | Post Review | Plan | 24-Jan-25 | 27-Jan-25 | NA | 27-Jan-25 | 10-Feb-25 | 14-Feb-25 | 17-Feb-25 | Plan | 10000 | 17-Feb-25 | 17-Feb-25 | 07-Mar-25 | N/A | 11-Mar-25 | 11-Mar-25
[8 empty] | Actual | [7 empty] | Actual
7 | Branding of ACEMFS for visibility | FUTM/ACEMFS/GDS/ST/2025/07 | 7 | 10000 | NS | Post Qualification | Post Review | Plan | 24-Jan-25 | 27-Jan-25 | NA | 27-Jan-25 | 10-Feb-25 | 14-Feb-25 | 17-Feb-25 | Plan | 10000 | 17-Feb-25 | 17-Feb-25 | 07-Mar-25 | N/A | 11-Mar-25 | 11-Mar-25
[8 empty] | Actual | [7 empty] | Actual
8 | Procurement and installation of Standby Generator Set | FUTM/ACEMFS/GDS/NCB/2025/08 | 1 | 20000 | NS | Post Qualification | Post Review | Plan | 24-Jan-25 | 27-Jan-25 | NA | 27-Jan-25 | 10-Feb-25 | 14-Feb-25 | 17-Feb-25 | Plan | 20000 | 17-Feb-25 | 17-Feb-25 | 07-Mar-25 | N/A | 11-Mar-25 | 14-Mar-25
[8 empty] | Actual | [7 empty] | Actual
9 | Procurement of SUV official Vehicle | FUTM/ACEMFS/GDS/NS/2025/09 | 2 | 60000 | NS | Post Qualification | Post Review | Plan | 16-Dec-24 | 06-Jan-25 | NA | 13-Jan-25 | 10-Feb-25 | 17-Feb-25 | 24-Feb-25 | Plan | 60000 | 24-Feb-25 | 25-Feb-25 | 19-Mar-25 | N/A | 11-Mar-25 | 11-Mar-25
[8 empty] | Actual | [7 empty] | Actual
10 | Procurement of research consumable/analysis for Food Safety, Toxicology, Molecular Biology and Bioinformatics | FUTM/ACEMFS/GDS/NS/2025/10 | 3 | 200000 | SELLECTIVE TENDERING | Pre Qualification | Post Review | Plan | 09-Dec-24 | 23-Dec-24 | NA | 30-Dec-24 | 10-Feb-25 | 17-Feb-25 | 24-Feb-25 | Plan | 200000 | 24-Feb-25 | 25-Feb-25 | 19-Mar-25 | N/A | 21-Mar-25 | 21-Mar-25
[8 empty] | Actual | [7 empty] | Actual
11 | Procurement of equipment for Food Safety, Molecular Biology and Bioinformatics, Nanotechnology and Toxicology (Biochip Array Technology) | FUTM/ACEMFS/GDS/NS/2025/11 | 1 | 300000 | SELLECTIVE TENDERING | Pre Qualification | Post Review | Plan | 09-Dec-24 | 23-Dec-24 | NA | 30-Dec-24 | 10-Feb-25 | 17-Feb-25 | 24-Feb-25 | Plan | 300000 | 24-Feb-25 | 25-Feb-25 | 19-Mar-25 | N/A | 21-Mar-25 | 28-Mar-25
[8 empty] | Actual | [7 empty] | Actual
| Total Cost |  |  | 633000 | [12 empty] | 633000
9741 | Fill gray cells only!

## Works
Country: NIGERIA
Program: ACE IMPACT
Date: December 2024
Applicable Period: January 2025 - JUNE, 2025
Project ID: ACEMFS FUT, Minna
| Implementing Agency: NUC, NIGERIA | [8 empty] | Draft Bid Documents, including specs and quantities, draft SPN |  | If Post-Review, No-objection Dates are not needed
|  |  | Basic Data | [8 empty] | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation |  |  | Contract Finalization |  |  |  | Contract Implementation
| Description* | Package Number | Lot Number | Lumpsum or Bill of Quantities | Procurement Method | Estimated Amount in US $ | Pre-or Post Qualification | Prior or Post Review | Plan vs. Actual | Prep & Submission by Ex Agency | No-objection Date | On-line UNDB Gateway Nat Press | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | No-objection Date | Plan vs. Actual | Contract Amount in US$ | Date Contract Award | Date Contract Advert | Date Contract Signature | Mobilization Advance Payment | Substantial Completion | Final Acceptance | Final Cost | REMARKS
| Norm Duration of Proc Steps | [5 empty] | If Prequalification |  | Plan | 4 - 7 wks | 1 - 1.5 wks | 1.5 - 2 wks | 1.5 - 2 wks | 6 to | 12 wks | 1.5 - 3 wks | Plan |  | 1 wk |  | 1.5-3 wks
[7 empty] | add 7-13 wks |  | Actual | [7 empty] | Actual
1 | General Maintenance of the centre's building | FUTM/ACEMFS/WKS/NCB/2025/01 | NA | BOQ | NCB | 20000 | Post Qualification | Post Review | Plan | 24-Jan-25 | 31-Jan-25 | NA | 07-Feb-25 | 07-Mar-25 | 14-Mar-25 | 17-Mar-25 | Plan | 20000 | 19-Mar-25 | 19-Mar-25 | 16-April-25 | N/A | 30-April-25 | 05-May-25 | 20000
[9 empty] | Actual | [7 empty] | Actual
| Total Cost |  |  |  |  | 20000 |  |  | Plan | [8 empty] | 20000 | [6 empty] | 20000
Actual
Fill gray cells only!
NB: Submission of BER under NCB implies submission by the Evaluation Committee to Management for Approval, and not to the Bank

## Services
Country/Organisation: NIGERIA / FEDERAL UNIVERSITY OF TECHNOLOGY, MINNA
Programme: ACE IMPACT
Date: DECEMBER, 2024
Applicable Period: JANUARY, 2025 - JUNE, 2025
Project ID: ACEMFS FUT, Minna
Credit Number:
Implementing Agency: NUC, NIGERIA
Request for EOI (where required)
| IDA Credit No.: |  | Contract Type |  |  |  | Preparation Request for Proposals |  |  |  | Short List |  |  | Consultant Proposals |  | Proposal Evaluation and Negotiation for Projects after May 2002 Technical (T) & Financial (F) and Negotions (N) | [5 empty] | Draft Contract |  | Contract Finalization |  |  |  |  | Contract Implementation |  |  |  | Remarks
| Description* | Selection Method | Lumpsum or Time-Based | Estimated Amount in US$ '000 | Prior/Post Review | Plan vs. Actual | Prep & Submission by Ex Ag | No-objection Date | On-line UNDB Gateway Nat Press | Lead-time before shortlist | Submission Date | No-objection Date | Plan vs. Actual | Invitation Date | Submission/ Opening Date | Submission Evaluation Report (T) | No-objection Evaluation Report (T) | Opening Financial Proposals | Preparation Eval Report (T) (F) | Negotiations (N) | Plan vs. Actual | Submission Date | No-objection Date | Contract Amount in US$ '000 | Contract Award | Date Contract Advert | Contract Signature | Plan vs. Actual | Mobilization Advance Payment | Draft Report | Final Report | Final Cost
| Norm Duration of Proc Steps |  |  |  |  | Plan | 3 - 6 wks | 1 - 2 wks | 1 - 1.5 wks | 2 wks |  | 1 - 2 wks | Plan | 4 to | 12 wks | 2 - 3 wks | 0.5 - 2 wks | 2 wks | 1 - 2 wks | 2 wks | Plan | 1 - 2 wks | 1 - 2 wks |  | 1 wk |  | 1 - 3 wks | Plan
Component 1:(Instititional Development)
2 | Upgrade of website | QCBS | Lump Sum | 10000 | Post Review | Plan | 02-Dec-24 | 13-Dec-24 | NA | 20-Dec-24 | 03-Jan-25 | 03-Jan-25 | Plan | 10-Jan-25 | 07-Feb-25 | 14-Feb-25 | 21-Feb-25 | 07-Mar-25 | 14-Mar-25 | 21-Mar-25 | Plan | 04-April-25 | 11-April-25 | 10000 | 18-April-25 | 25-April-25 | 02-May-25 | Plan | N/A | 09-May-25 | 14-May-25 | 10000
[6 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
2 | NgREN Subscription | QCBS | Lump Sum | 100000 | Post Review | Plan | 02-Dec-24 | 13-Dec-24 | NA | 20-Dec-24 | 03-Jan-25 | 03-Jan-25 | Plan | 10-Jan-25 | 07-Feb-25 | 14-Feb-25 | 21-Feb-25 | 07-Mar-25 | 14-Mar-25 | 21-Mar-25 | Plan | 04-April-25 | 11-April-25 | 100000 | 18-April-25 | 25-April-25 | 02-May-25 | Plan | N/A | 09-May-25 | 14-May-25 | 100000
[6 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
| TOTAL AMOUNT |  |  | 110000 | [19 empty] | 110000 | [7 empty] | 110000