## Sheet1
Name of Center | AFRICA CENTRE OF EXCELLENCE FOR MYCOTOXIN AND FOOD SAFETY
Institution | FEDERAL UNIVERSITY OF TECHNOLOGY, MINNA |  |  | On Schedule
Country | NIGERIA
Center Leader | PROFESSOR HUSSAINI ANTHONY MAKUN |  |  | Behind Schedule
Annual Workplan (Month XXX-Month XXX, Year) | JANUARY 2025-JUNE 2025
Work Plan Activities | Description | Partner Contribution (if relevant) | 2025 Y5Q1 |  |  | 2025 Y5Q2 |  |  | 2025 Y5Q3 |  |  | 2025 Y5Q4 |  |  | Milestone/Output | If NEW, Provide Justification | Estimated Budget($) | Estimated Revenue ($) | Contribution from Partner ($) | Person Responsible
|  |  | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
Action 1:Quality Education
Sub-Action 1a: Launch Workshop/Curricular Review for M.Tech and PhD in Food Safety, Molecular Biology and Bioinformatics and Toxicology
Activity 1: Gather ACEMFS team and engage partners and stakeholders to review the curriculum for MTech and PhD in Food Safety, Molecular Biology and Bioinformatics, and Toxicology | Bring together ACEMFS team, partners and stakeholders to a launch workshop.ACEMFS together with partners and stakeholders will review the curricular for Mtech and PhD in Food Safety, Molecular Biology and Bioinformatics and Toxicology, advise on purchase and maintance of eqiupment and internship at the Launch workshop | [13 empty] | The reviewed curriculum will be adopted if no major changes from the existing one, but else will be sent to the Senate for approval if there are major changes |  | 5000 |  |  | ACEMFS Team,ISAB and SAB
Sub-Action 1b: Scholarship for national and regional students
Activity 1: Scholarships to already existing students | Scholarship obligations will be fulfilled to existing ACEMFS students on full scholarship for the session | [13 empty] | All financial obligations to students on scholarship will be fulfilled. It can be verified by the scholarship award letters and from the bank statement. |  | 200000 | 5000 |  | ACEMFS Team
Sub-Action 1c: Short term visits by experts/partners from collaborating insitutions and organisations
Activity 1: Meeting of ACEMFS team, Sectorial Advisory Board and the International Scientific Advisory Board. | Meetings will be held between the Centre and its partners to strengthen collaborations, monitor and evaluate collaborations . | [13 empty] | Invitation will be extended to ASB, ISAB,the NUC and the AAU. |  | 60000 |  |  | ACEMFS Team/Partners
Sub-Action 1e: Procurement of Teaching consumables for Food Safety, Toxicology and Molecularbiology and Bioinformatics
Activity 1: Provide adequate teaching materials and facilities for Food Safety, Molecular Biology and Bioinformatics, and Toxicology | Provide adequate teaching materials and facilities for Food Safety, Molecular Biology and Bioinformatics,and Toxicology i.e the Big blue Button and the server licence fees | [13 empty] | •Identification of sources of quality laboratory/equipment consumables •Procurement of consumables |  | 5000 |  |  | Centre leader,Procurement Officer, Project Accountant
Sub-Action 1f: Accreditation
Activity 1: International accreditation of ACEMFS Programmes. | The Centre will continue with the International Programs accreditation. | [13 empty] | Accreditation Letters by the accrediting body for the Centre Programs accreditation |  | 100000 |  |  | FUT Minna Management and ACE Team
Activity 2: International Institutional Accreditation of the University (FUT Minna). | The Centre will continue with the international institutional accreditation for the university. | [13 empty] | Accreditation Letters by the accrediting body for the Centre Institutional accreditation |  | 125000
Action 2:Quality Applied Research
Sub-Action 2a: Procurement of research consumables/reagents for Food Safety, Toxicology and Molecularbiology and Bioinformatics
Activity 1: Procurement of research consumables/reagents for Food Safety, Toxicology, Molecular Biology and Bioinformatics | Procurement would be carried out strictly in conformity to the Nigerian laws on procurement. | [13 empty] | •Preparation, tendering , selection and award of contract at 1st quarter, 2025 |  | 200000 | 5000 |  | Centre Leader, Procurement Officer
Sub-Action 2b: Short term training/workshops/conferences for ACEMFS academic faculties
Activity 1: Academic faculties and Partners will attend both local and International conferences for knowledge update | The Academic Faculties and partners will attend field related workshops, seminars and conferences. | [13 empty] | Workshops and conferences as capacity building for faculty members. |  | 60000 |  |  | Centre Leader, Project Coordinator/Training Coordinator
Activity 2: Seminar Attendance at the Food and Agricultural Organization (FAO), United Nations World Food Summit, World Food Programme (WFP) | Some of the centre's academic officers will attend workshops/seminars/conferences in food safety in Europe. | [15 empty] | 60000 |  |  | ACEMFS Team
Activity 3: Seed Grant Scheme | Provision of one time seed grant and establishment of start-ups and spin-offs to address challenges in food safety.Winners will be selected on a competitive basis. | [13 empty] | This will support development of early stage ventures with high potential for positive impact of food safety in Africa. |  | 5000 |  |  | ACEMFS Team and Entreprenuership Centre
Sub-Action 2c: Sampling of food crops and feed for mycotoxins and other contaminants analysis
Activity 1: Field work/Sampling | Sampling will be carried out at identified locations regionally and nationally | [13 empty] | Codex report on food standard |  | 20000 |  |  | ACEMFS Team, Partners, Project Management Team
Sub-Action 2d: Publications with Partners in internationally recognised journals
Activity 1: Publish in High Impact (international) journals | Research work from the Centre will only be published in internationally recognised journals | [13 empty] | Production of journals |  | 15000 |  |  | ACEMFS Team
Action 3: Improved Learning Environment
Sub-Action 3a: Meeting milestones for improved learning and research environment specified in the performance and funding contracts
Activity 1:General Maintenance of the centre's building | General Maintenance of the centre's building | [15 empty] | 20000 |  |  | ACEMFS Team
Activity 2: Maintenance of Inverter battery cells/Accessories | Already installed solar panels will be maintained for optimal service | [15 empty] | 10000 |  |  | ACEMFS Team
Activity 3 : Procurement of 1 MIKANO generator | Procurement of 1 generator as alternative source of power | [15 empty] | 20000 |  |  | ACEMFS Team
Acitvity 4: Purchase of Toyota Fortuna vehicle | The centre will procure a Toyota Fortuna car as an official car for the Centre Leader. | [15 empty] | 60000 |  |  | ACEMFS Team
Sub-Action 3b: Procurement of equipment for Food Safety, Molecular Biology and Bioinformatics and Nanotechnology
Activity 1: Procurement of equipment for Food Safety, Molecular Biology and Bioinformatics, Nanotechnology and Toxicology (Biochip Array Technology) | Centre will prepare all documents and follow the procedure necessary for procurement of additional equipment for the programmes of the Centre. | [13 empty] | • Preparation and tendering through advert, • Selection and award of contract procurement of equipments |  | 300000 | 5000 |  | Centre Leader, Procurement Officer
Action 4: Efficient Management
Sub-Action 4a: Production of Manuals and purchase of office equipment
Activity 1: Purchase of office equipment | Purchase of cabinets, fireproof Safe, Shelves and fridges, water dispensers e.t.c | [15 empty] | 10000 |  |  | ACEMFS Team
Activity 2: Publish manuals and student handbooks | Hardcopies of all manuals and student handbooks will be published and distributed to faculty and students. | [13 empty] | • Produce Procurement, Financial Management, ESSG, M&E Operational Manual and student handbook |  | 5000 |  |  | ACEMFS Team
Sub-Action 4b:ACE National and Regional Workshops
Activity 1: Meeting of all ACE Centres, general Workshops and specialisation workshop | All Officers will attend the biannual regional and national workshops for ACE,area of specialisation workshops . | [13 empty] | Effective and efficient capacity development for ACEMFS resulting in enhanced capacities of trainees in key management tools and techniques.12 core officers of ACEMFS will attend ACE workshops twice in a year and other workshops organised by the AAU. |  | 70000 |  |  | Centre leader, Project Accountant, Auditor, Procurement Officer
Sub-Action 4c: General Administration
Activity 1: Office supplies and equipment (maintenace and purchase), reports and other consumables | Allocation of resources to meet specific needs within the centre | [13 empty] | •Allocation of resources to specific needs under communication, office equipment, travels, meetings, reports and consumables • Purchase |  | 10000 |  |  | ACEMFS Team
Activity 2: Weekly and out station meetings | Centre meetings will hold once in a week | [13 empty] | Regular meetings will provide an avenue to discuss the challenges and acheivements of the centre. |  | 10000 |  |  | ACEMFS Team
Activity 3: Courier and postage services | For effective delivery of mails, the Centre will use the services of courier | [13 empty] | Certificates will be sent to regional students that will not be on ground for collection after convocation, research samples with special needs will be sent to other laboratories for analysis. |  | 5000 |  |  | ACEMFS Team
Activity 4: Official vehicle maintenance and fuelling | The vehicle will be maintained and fuelled as is needed | [15 empty] | 20000 |  |  | Centre Leader, Procurement Officer,Project Accountant
Activity 5: Support for online/virtual activities | Support will be provided for all activties the Centre engages in | [15 empty] | 5000 |  |  | ACEMFS Team
Activity 6: Bank charges | Bank charges would need to be paid | [15 empty] | 2000 |  |  | Finance Team
Activity 7: Branding of ACEMFS for visibility | The centre will produce, lab coats, T-Shirts, Jotters, Blazers, reflector jackets, wrappers, keyholders, water flasks, laptop bags e.t.c to advertise the centre and its objectives to her immediate and external environment | [13 empty] | Branding will create awareness and the items will serve as sovenirs to visitior. |  | 10000 |  |  | ACEMFS Team
Activity 8: Preparation of final report /project closure activities | Some key ACEMFS officers will pull out to Abuja to ensure full concentration for the preparation of final report / project closure activities | [15 empty] | 30000 |  |  | Centre Leader, Deputy Centre Leader, M & E officer, project accountant and procurement officer
Sub-Action 4e: Fiduciary Enhancement
Activity 1: Conduct audit of accounts | The Centre will invite auditors to audit its accounts | [13 empty] | Periodic audit is a requirement that must be fulfiled to enable the centre make submission for DLI 6 |  | 2000 |  |  | Finance Team
Sub-Action 4f: Relevant training/workshop by ACEMFS staff and partners
Activity 1: Train ACEMFS staff and partners | The Centre will identify necessary trainings for its staff and partners | [13 empty] | Training of ACEMFS staff and partners.Especially on sustainability. |  | 120000 |  |  | ACEMFS Team
Activity 2: Ensuring participation of University Management/Directors of Units supporting the Centre | Identify relevant workshops for University Management personnel and Directors of units supporting the Centre to foster participation of University Management in Centre's activities | [15 empty] | 40000 |  |  | Centre Leader,Vice Chancellor
Activity 5: Conference on PMP certification by Project Accountant, Secretary, M&E Officer and Deputy Centre Leader, Procurement officer, Auditor, Environmental and social safeguard officer,Assistant Project Accountant,Finance Officer and Communication officer | Attend and write exams for PMP certification | [15 empty] | 10000
Action 5: Communication
Activity 1: Awareness, Advocacy, and ACEMFS fair | Create awareness to the Centre through fairs, radio/TV jingle, newsletters locally and internationally | [13 empty] | Adequate information on effects and control of mycotoxins and other contaminants in foods and feeds |  | 3000 |  |  | ACEMFS Team, ICT/Communication officer
Activity 2: Upgrade website | [16 empty] | 10000 |  |  | ACEMFS Team, ICT/Communication officer
Activity 3: Purchase camera | The Centre will purchase a digital camera to cover all Centre events | [15 empty] | 3000 |  |  | ACEMFS Team, ICT/Communication officer
Action 7\ DLI 1 7 Action:Institutional Impact
Sub-Action 1: ICT Services from NUC (NgREN)
Activity 1: Maintain subscription to NgREN | Subscription to NgREN to be maintained by the Centre | [15 empty] | 100000 |  |  | NUC and ACEMFS Team
TOTAL | [16 empty] | 1730000 | 15000